## Mar 24
CR # | CR Description | Priority | *Proposed Deployment Date
PRMO-1523 | MMIS Electronic Data Interchange (834): Sending Managed care updates and terminations to M3G from PRMMIS | Critical | October 2023
PRMO-4253 | Replace notice: Expiration of eligibility | Critical | October 2023
PRMO-4854 | Validate Hacienda Response Codes Updates | Critical | October 2023
PRMO-3388 | Disposition of caseworker activities for Renewals unwinding after Public Health Emergency (PHE) | Critical | November 2023
PRMO-3722 | Maintenance of Evidence coming into M3G from Interfaces | Critical | December 2023
PRMO-2637 | "No Touch" Renewals and CoCs | Critical | July 2024
PRMO-4133 | All Non-MAGI Case Determinations Are Out Of Compliance | Critical | May 2024
PRMO-4301 | Redeterminations of all Cases From July 1, 2023 through the date PRMO-4287 is Deployed | Critical | March 2024
PRMO-4511 | Allow for Manual Recertification outside of the current Recertification Period | Critical | March 2024
PRMO-4512 | Modify how Reasonable Compatibility is applied to data received from the interfaces | Critical | March 2024
PRMO-4980 | Critical Care Beneficiaries Eligibility through April 30, 2024 | Critical | November 2023
PRMO-5147 | Continuous Eligibility to Children in Medicaid and CHIP | Critical | March 2024
PRMO-2635 | "No Touch" Initial Application - No Caseworker Intervention | Critical | July 2024
PRMO-3238 | Report of all members currently receiving TANF | Critical | Not Applicable
PRMO-4297 | Effective Coverage Date for Renewal Determined Eligible During Reconsideration Period | Critical | March 2024
PR-15357 | Additional Scope: Auto-Enroll TANF Recipients within MEDITI3G (PRMO-791) | High | March 2024
PRMO-3237 | Notice of Decisions for Ex Parte Process | Critical | May 2024
PRMO-2198 | MMIS/ASES _Daily/Recon Interface Notification Report | High | December 2023
PRMO-3190 | Verify Current Income H138 upgrade to REST/JSON RJ138 | High | October 2023
PRMO-3191 | RIDP./FARS (H139/H140) upgrade from SOAP to REST/JSON (RJ139/RJ140) | High | October 2023
PRMO-3584 | Creation of Group 8 Field | High | October 2023
PRMO-3576 | Group ID Modification CR | High | March 2024
PRMO-3662 | Modify the Renewal Notification letter | High | May 2024
PRMO-1517 | Police Safety Net Changes | High | March 2024
PRMO-4508 | Establishment of Dedicated Production-Like Data Testing Environment | High | March 2024
PR-13737 | EE-CR00083 Interface Between PREE and ASUME | High | May 2024
PRMO-4215 | Changes to Recertification Process for No Shows | High | December 2023
PRMO-4606 | Transitional Medicaid Functionality | High | Not Scheduled
PR-13738 | EE-CR00084 Interface Between MEDITI3G and DRNA | High | July 2024
PR-13811 | EE-CR00195 DTOP Interface | High | September 2024
PRMO-1452 | Language Update SSN Instructions | High | May 2024
PRMO-2639 | Masking of SSN, Passport ID, and any other sensitive fields. | High | May 2024
PRMO-2650 | Certifying Authority for Electronic Signature | High | September 2024
PRMO-4300 | Medicaid Eligible for Defined Groups | High | Not Applicable
PRMO-4306 | Add 4 Months of Coverage for Individuals who Lose Coverage due to an Increase in Spousal Support | High | May 2024
PRMO-3386 | Second Level Appeals Notice | High | May 2024
PR-16284 | Upgrade to Curam V8 | Medium | Not Applicable
PRMO-1020 | Audit/QC - Outlier Report (CR-219) - Design Only | Medium | March 2024
PRMO-1426 | Retroactive Coverage Cannot Be Restricted Only to Services That Are Unpaid | Medium | July 2024
PRMO-1521 | Veteran Status | Medium | July 2024
PRMO-1560 | Physical address should not be required | Medium | Not Scheduled
PRMO-1562 | Process App when Applicant Does not Recall SSN | Medium | May 2024
PRMO-1615 | The Audit Quality Control Focus Area Findings Visibility | Medium | Not Scheduled
PRMO-1767 | American Indian and Alaska Native Changes | Medium | Not Scheduled
PRMO-1817 | Change the Alien Status list | Medium | Not Scheduled
PRMO-1818 | Non-Magi Questions are Optional | Medium | July 2024
PRMO-1839 | New Fields for Alien Number and Certificate Number | Medium | July 2024
PRMO-1840 | Retroactive Vs Current Application - Residency | Medium | July 2024
PRMO-1841 | Retro and Home Relationships | Medium | Not Scheduled
PRMO-1842 | Add 'Other' as a value for the Frequency Code Table | Medium | Not Scheduled
PRMO-1843 | Non-MAGI Questions | Medium | July 2024
PRMO-1844 | Non-MAGI Question on Employment | Medium | May 2024
PRMO-1845 | MAGI Income Deductions and Non-MAGI Expenses | Medium | May 2024
PRMO-1931 | Retro Employment Questions | Medium | September 2024
PRMO-1932 | Retro Self Employment | Medium | September 2024
PRMO-1933 | Alimony as Income Based on Date Divorce Finalized or Modified | Medium | May 2024
PRMO-1934 | Retro Benefits | Medium | September 2024
PRMO-1935 | Retro Other Income | Medium | September 2024
PRMO-1936 | Retro Other Expenses | Medium | September 2024
PRMO-1937 | Retro Trust Income | Medium | Not Scheduled
PRMO-1938 | Retro Annuity Income Details | Medium | Not Scheduled
PRMO-1939 | Non-MAGI Income Based on Current Month | Medium | October 2023
PRMO-1940 | Update Income Frequency to Match Paper Application | Medium | May 2024
PRMO-1941 | Income Information Updates for MAGI/Non-MAGI | Medium | July 2024
PRMO-1942 | Adult and Children Trust and Annuity Income Counted for Non-MAGI | Medium | July 2024
PRMO-2199 | Availability for Consolidate offices with System Admins role | Medium | July 2024
PRMO-2211 | Remove Expense Detail from Retro Application | Medium | September 2024
PRMO-2399 | M3G Query - Individuals affected by a negative change | Medium | Not Scheduled
PRMO-2415 | Authorized Representative Functionality in Citizen Portal | Medium | Not Scheduled
PRMO-2774 | Virtual Region under MMM (MCO) - Validation | Medium | December 2023
PRMO-3023 | ADFAN Interface Match Critera | Medium | December 2023
PRMO-3105 | "Submit" Needs to Trigger Electronic Verifications Call | Medium | July 2024
PRMO-3260 | Use TANF Income as Verified Income for Renewals and Auto Enroll TANF Clients | Medium | December 2023
PRMO-4266 | Recon file with ASES before 834 GOLIVE | Medium | Not Scheduled
PRMO-466 | Audit/QC - Marked Samples Report | Medium | Not Scheduled
PRMO-467 | Audit/QC - Indicator Report | Medium | Not Scheduled
PRMO-56 | In the prod-ua.preeservices.com website the tab says "Servicios Sociales" | Medium | Not Scheduled
PRMO-2528 | Ability to have Automatic Enrollment without CW intervention | Low | Not Scheduled
PRMO-2529 | Correct Reminder Notice for ROP documentation not being sent to applicants | Low | Not Scheduled
PRMO-2530 | PR Correctional Department Interface implementation | Low | Not Scheduled
PRMO-2531 | Remove the risk level field on individual’s eligibility status if it has no significance or impact | Low | Not Scheduled
PRMO-2610 | Members with a DOD entered with active PDC previous the implementation of CR-PRMO-1489 | Low | Not Scheduled
PRMO-3110 | Exceptions to negative changes in eligibility and coverage codes for children under 21 and pregnant women | Low | March 2024
PRMO-3259 | Adverse Action Notices | Low | Not Scheduled
PRMO-3375 | Implement the VLP Interface to Verify Lawful Presence | Low | September 2024
TBD | Real-Time Interfaces | High | May 2024
PRMO-467 | Audit/QC - Indicator Report | Medium | Not Scheduled
*As of February 2024

## May 24
CR # | CR Description | Priority | Amend H Top 22? | Proposed Deployment Date
PRMO-4133 | All Non-MAGI Case Determinations Are Out Of Compliance | Critical | N | May 2024
PRMO-3237 | Notice of Decisions for Ex Parte Process | Critical | Y | May 2024
PRMO-3662 | Modify the Renewal Notification letter | High | N | May 2024
PR-13737 | EE-CR00083 Interface Between PREE and ASUME | High | Y | May 2024
PRMO-1452 | Language Update SSN Instructions | High | N | May 2024
PRMO-2639 | Masking of SSN, Passport ID, and any other sensitive fields. | High | Y | May 2024
PRMO-4306 | Add 4 Months of Coverage for Individuals who Lose Coverage due to an Increase in Spousal Support | High | N | May 2024
PRMO-3386 | Second Level Appeals Notice | High | N | May 2024
PRMO-1562 | Process App when Applicant Does not Recall SSN | Medium | N | May 2024
PRMO-1844 | Non-MAGI Question on Employment | Medium | N | May 2024
PRMO-1845 | MAGI Income Deductions and Non-MAGI Expenses | Medium | N | May 2024
PRMO-1933 | Alimony as Income Based on Date Divorce Finalized or Modified | Medium | N | May 2024
PRMO-1940 | Update Income Frequency to Match Paper Application | Medium | N | May 2024
TBD | Real-Time Interfaces | High | N | May 2024

## July 24
CR # | CR Description | Priority | Amend H Top 22? | Proposed Deployment Date
PRMO-2637 | "No Touch" Renewals and CoCs | Critical | Y | July 2024
PRMO-2635 | "No Touch" Initial Application - No Caseworker Intervention | Critical | Y | July 2024
PR-13738 | EE-CR00084 Interface Between MEDITI3G and DRNA | High | Y | July 2024
PRMO-1426 | Retroactive Coverage Cannot Be Restricted Only to Services That Are Unpaid | Medium | N | July 2024
PRMO-1521 | Veteran Status | Medium | N | July 2024
PRMO-1818 | Non-Magi Questions are Optional | Medium | N | July 2024
PRMO-1839 | New Fields for Alien Number and Certificate Number | Medium | N | July 2024
PRMO-1840 | Retroactive Vs Current Application - Residency | Medium | N | July 2024
PRMO-1843 | Non-MAGI Questions | Medium | N | July 2024
PRMO-1941 | Income Information Updates for MAGI/Non-MAGI | Medium | N | July 2024
PRMO-1942 | Adult and Children Trust and Annuity Income Counted for Non-MAGI | Medium | N | July 2024
PRMO-2199 | Availability for Consolidate offices with System Admins role | Medium | N | July 2024
PRMO-3105 | "Submit" Needs to Trigger Electronic Verifications Call | Medium | N | July 2024

## Sep 24
CR # | CR Description | Priority | Amend H Top 22? | Proposed Deployment Date
PR-13811 | EE-CR00195 DTOP Interface | High | Y | September 2024
PRMO-2650 | Certifying Authority for Electronic Signature | High | Y | September 2024
PRMO-1931 | Retro Employment Questions | Medium | N | September 2024
PRMO-1932 | Retro Self Employment | Medium | N | September 2024
PRMO-1934 | Retro Benefits | Medium | N | September 2024
PRMO-1935 | Retro Other Income | Medium | N | September 2024
PRMO-1936 | Retro Other Expenses | Medium | N | September 2024
PRMO-2211 | Remove Expense Detail from Retro Application | Medium | N | September 2024
PRMO-3375 | Implement the VLP Interface to Verify Lawful Presence | Low | NA | September 2024